## Overview_Weekly
calendar_week | worklog_author | total_hours
2026-W37 | Anton Hedlund | 3
2026-W37 | Calvin Koch | 5
2026-W37 | Einar Eriksson Wahlin | 0
2026-W37 | Klas Widebeck | 5
2026-W37 | Sai Suchith Kurra | 5.5
2026-W37 | Seleman Hassan | 0
2026-W38 | Anton Hedlund | 5
2026-W38 | Calvin Koch | 5
2026-W38 | Einar Eriksson Wahlin | 5.5
2026-W38 | Klas Widebeck | 5
2026-W38 | Sai Suchith Kurra | 4.5
2026-W38 | Seleman Hassan | 5
2026-W39 | Anton Hedlund | 7.25
2026-W39 | Calvin Koch | 8.5
2026-W39 | Einar Eriksson Wahlin | 6
2026-W39 | Klas Widebeck | 8
2026-W39 | Sai Suchith Kurra | 8
2026-W39 | Seleman Hassan | 7.5
2026-W40 | Anton Hedlund | 6
2026-W40 | Calvin Koch | 5.5
2026-W40 | Einar Eriksson Wahlin | 5.5
2026-W40 | Klas Widebeck | 5
2026-W40 | Sai Suchith Kurra | 8.5
2026-W40 | Seleman Hassan | 5
2026-W41 | Anton Hedlund | 6.5
2026-W41 | Calvin Koch | 5.5
2026-W41 | Einar Eriksson Wahlin | 5.5
2026-W41 | Klas Widebeck | 5.5
2026-W41 | Sai Suchith Kurra | 7.5
2026-W41 | Seleman Hassan | 5

## Overview_Sprint
sprint_by_date | worklog_author | total_hours
SCRUM Sprint 1 | Anton Hedlund | 3
SCRUM Sprint 1 | Calvin Koch | 5
SCRUM Sprint 1 | Klas Widebeck | 5
SCRUM Sprint 1 | Sai Suchith Kurra | 5.5
SCRUM Sprint 2 | Anton Hedlund | 12.25
SCRUM Sprint 2 | Calvin Koch | 13.5
SCRUM Sprint 2 | Einar Eriksson Wahlin | 11.5
SCRUM Sprint 2 | Klas Widebeck | 13
SCRUM Sprint 2 | Sai Suchith Kurra | 12.5
SCRUM Sprint 2 | Seleman Hassan | 12.5
SCRUM Sprint 3 | Anton Hedlund | 12.5
SCRUM Sprint 3 | Calvin Koch | 11
SCRUM Sprint 3 | Einar Eriksson Wahlin | 11
SCRUM Sprint 3 | Klas Widebeck | 10.5
SCRUM Sprint 3 | Sai Suchith Kurra | 16
SCRUM Sprint 3 | Seleman Hassan | 10

## Fact_Timelogs
worklog_id | timestamp | date | calendar_week | sprint_by_date | worklog_author | author_id | issue_key | hours_logged | comment
10842 | 2026-10-01 14:33:00 | 2026-10-01 | 2026-W40 | SCRUM Sprint 3 | Klas Widebeck | 712020:ba6fc434-9839-4353-a732-a8f4b60b9695 | SCRUM-90 | 4
10951 | 2026-10-05 13:22:00 | 2026-10-05 | 2026-W41 | SCRUM Sprint 3 | Klas Widebeck | 712020:ba6fc434-9839-4353-a732-a8f4b60b9695 | SCRUM-90 | 1
10708 | 2026-10-08 19:05:06 | 2026-10-08 | 2026-W41 | SCRUM Sprint 3 | Sai Suchith Kurra | 712020:7a155d42-06e0-4222-9d4e-f39dede68758 | SCRUM-88 | 1
10741 | 2026-10-08 16:48:20 | 2026-10-08 | 2026-W41 | SCRUM Sprint 3 | Sai Suchith Kurra | 712020:7a155d42-06e0-4222-9d4e-f39dede68758 | SCRUM-85 | 5
10638 | 2026-10-07 10:43:05 | 2026-10-07 | 2026-W41 | SCRUM Sprint 3 | Calvin Koch | 712020:1793fffe-a3b4-4b8b-b162-77b2e79e19da | SCRUM-84 | 1
10844 | 2026-10-09 18:38:00 | 2026-10-09 | 2026-W41 | SCRUM Sprint 3 | Klas Widebeck | 712020:ba6fc434-9839-4353-a732-a8f4b60b9695 | SCRUM-84 | 2
10986 | 2026-10-09 08:28:00 | 2026-10-09 | 2026-W41 | SCRUM Sprint 3 | Anton Hedlund | 712020:991ea2e9-c055-4d6e-a6b7-a44bccafe0a6 | SCRUM-84 | 0.5
10635 | 2026-10-07 10:22:37 | 2026-10-07 | 2026-W41 | SCRUM Sprint 3 | Calvin Koch | 712020:1793fffe-a3b4-4b8b-b162-77b2e79e19da | SCRUM-83 | 1.5
10639 | 2026-10-07 10:52:19 | 2026-10-07 | 2026-W41 | SCRUM Sprint 3 | Sai Suchith Kurra | 712020:7a155d42-06e0-4222-9d4e-f39dede68758 | SCRUM-83 | 1.5
10640 | 2026-10-07 10:52:19 | 2026-10-07 | 2026-W41 | SCRUM Sprint 3 | Seleman Hassan | 712020:7e8593ee-4747-44a1-89c2-28e81af19f99 | SCRUM-83 | 1.5
10641 | 2026-10-07 10:52:40 | 2026-10-07 | 2026-W41 | SCRUM Sprint 3 | Einar Eriksson Wahlin | 712020:873506cb-9f09-47b4-8689-67e320ded9be | SCRUM-83 | 1.5
10845 | 2026-10-07 11:00:00 | 2026-10-07 | 2026-W41 | SCRUM Sprint 3 | Klas Widebeck | 712020:ba6fc434-9839-4353-a732-a8f4b60b9695 | SCRUM-83 | 1.5
10404 | 2026-09-29 07:20:10 | 2026-09-29 | 2026-W40 | SCRUM Sprint 3 | Sai Suchith Kurra | 712020:7a155d42-06e0-4222-9d4e-f39dede68758 | SCRUM-82 | 4
10370 | 2026-09-21 19:00:00 | 2026-09-21 | 2026-W39 | SCRUM Sprint 2 | Calvin Koch | 712020:1793fffe-a3b4-4b8b-b162-77b2e79e19da | SCRUM-80 | 2
10368 | 2026-09-28 17:56:13 | 2026-09-28 | 2026-W40 | SCRUM Sprint 3 | Calvin Koch | 712020:1793fffe-a3b4-4b8b-b162-77b2e79e19da | SCRUM-79 | 3
10775 | 2026-10-09 00:45:44 | 2026-10-09 | 2026-W41 | SCRUM Sprint 3 | Anton Hedlund | 712020:991ea2e9-c055-4d6e-a6b7-a44bccafe0a6 | SCRUM-78 | 3
10774 | 2026-10-09 01:45:26 | 2026-10-09 | 2026-W41 | SCRUM Sprint 3 | Anton Hedlund | 712020:991ea2e9-c055-4d6e-a6b7-a44bccafe0a6 | SCRUM-77 | 2
10322 | 2026-09-28 11:00:24 | 2026-09-28 | 2026-W40 | SCRUM Sprint 3 | Anton Hedlund | 712020:991ea2e9-c055-4d6e-a6b7-a44bccafe0a6 | SCRUM-75 | 1
10323 | 2026-09-28 11:00:25 | 2026-09-28 | 2026-W40 | SCRUM Sprint 3 | Klas Widebeck | 712020:ba6fc434-9839-4353-a732-a8f4b60b9695 | SCRUM-75 | 1
10324 | 2026-09-28 11:00:30 | 2026-09-28 | 2026-W40 | SCRUM Sprint 3 | Seleman Hassan | 712020:7e8593ee-4747-44a1-89c2-28e81af19f99 | SCRUM-75 | 1
10325 | 2026-09-28 11:00:28 | 2026-09-28 | 2026-W40 | SCRUM Sprint 3 | Calvin Koch | 712020:1793fffe-a3b4-4b8b-b162-77b2e79e19da | SCRUM-75 | 1
10365 | 2026-09-28 11:00:00 | 2026-09-28 | 2026-W40 | SCRUM Sprint 3 | Sai Suchith Kurra | 712020:7a155d42-06e0-4222-9d4e-f39dede68758 | SCRUM-75 | 1
10470 | 2026-09-28 11:00:00 | 2026-09-28 | 2026-W40 | SCRUM Sprint 3 | Einar Eriksson Wahlin | 712020:873506cb-9f09-47b4-8689-67e320ded9be | SCRUM-75 | 1.5
10363 | 2026-09-10 19:30:00 | 2026-09-10 | 2026-W37 | SCRUM Sprint 1 | Calvin Koch | 712020:1793fffe-a3b4-4b8b-b162-77b2e79e19da | SCRUM-74 | 1
10642 | 2026-10-07 11:22:56 | 2026-10-07 | 2026-W41 | SCRUM Sprint 3 | Einar Eriksson Wahlin | 712020:873506cb-9f09-47b4-8689-67e320ded9be | SCRUM-73 | 1
10675 | 2026-10-05 13:00:00 | 2026-10-05 | 2026-W41 | SCRUM Sprint 3 | Anton Hedlund | 712020:991ea2e9-c055-4d6e-a6b7-a44bccafe0a6 | SCRUM-71 | 1
10846 | 2026-10-05 13:00:00 | 2026-10-05 | 2026-W41 | SCRUM Sprint 3 | Klas Widebeck | 712020:ba6fc434-9839-4353-a732-a8f4b60b9695 | SCRUM-71 | 1
10602 | 2026-10-05 13:00:00 | 2026-10-05 | 2026-W41 | SCRUM Sprint 3 | Einar Eriksson Wahlin | 712020:873506cb-9f09-47b4-8689-67e320ded9be | SCRUM-70 | 1
10879 | 2026-09-23 12:00:00 | 2026-09-23 | 2026-W39 | SCRUM Sprint 2 | Einar Eriksson Wahlin | 712020:873506cb-9f09-47b4-8689-67e320ded9be | SCRUM-68 | 1.5
10503 | 2026-10-01 09:00:00 | 2026-10-01 | 2026-W40 | SCRUM Sprint 3 | Einar Eriksson Wahlin | 712020:873506cb-9f09-47b4-8689-67e320ded9be | SCRUM-67 | 1.5
10569 | 2026-10-05 07:49:53 | 2026-10-05 | 2026-W41 | SCRUM Sprint 3 | Einar Eriksson Wahlin | 712020:873506cb-9f09-47b4-8689-67e320ded9be | SCRUM-67 | 2
10636 | 2026-10-02 11:40:00 | 2026-10-02 | 2026-W40 | SCRUM Sprint 3 | Calvin Koch | 712020:1793fffe-a3b4-4b8b-b162-77b2e79e19da | SCRUM-67 | 1.5
10637 | 2026-10-07 09:42:30 | 2026-10-07 | 2026-W41 | SCRUM Sprint 3 | Calvin Koch | 712020:1793fffe-a3b4-4b8b-b162-77b2e79e19da | SCRUM-67 | 2
10916 | 2026-10-08 08:20:00 | 2026-10-08 | 2026-W41 | SCRUM Sprint 3 | Calvin Koch | 712020:1793fffe-a3b4-4b8b-b162-77b2e79e19da | SCRUM-66 | 1
10917 | 2026-10-02 07:54:00 | 2026-10-02 | 2026-W40 | SCRUM Sprint 3 | Seleman Hassan | 712020:7e8593ee-4747-44a1-89c2-28e81af19f99 | SCRUM-66 | 1.5
10918 | 2026-10-09 07:24:00 | 2026-10-09 | 2026-W41 | SCRUM Sprint 3 | Seleman Hassan | 712020:7e8593ee-4747-44a1-89c2-28e81af19f99 | SCRUM-66 | 2
10176 | 2026-09-24 11:13:09 | 2026-09-24 | 2026-W39 | SCRUM Sprint 2 | Einar Eriksson Wahlin | 712020:873506cb-9f09-47b4-8689-67e320ded9be | SCRUM-64 | 1
10177 | 2026-09-24 11:13:09 | 2026-09-24 | 2026-W39 | SCRUM Sprint 2 | Sai Suchith Kurra | 712020:7a155d42-06e0-4222-9d4e-f39dede68758 | SCRUM-64 | 1
10178 | 2026-09-24 11:13:15 | 2026-09-24 | 2026-W39 | SCRUM Sprint 2 | Calvin Koch | 712020:1793fffe-a3b4-4b8b-b162-77b2e79e19da | SCRUM-64 | 1
10179 | 2026-09-24 11:13:10 | 2026-09-24 | 2026-W39 | SCRUM Sprint 2 | Seleman Hassan | 712020:7e8593ee-4747-44a1-89c2-28e81af19f99 | SCRUM-64 | 1
10180 | 2026-09-24 11:14:22 | 2026-09-24 | 2026-W39 | SCRUM Sprint 2 | Klas Widebeck | 712020:ba6fc434-9839-4353-a732-a8f4b60b9695 | SCRUM-64 | 1
10319 | 2026-09-24 10:53:00 | 2026-09-24 | 2026-W39 | SCRUM Sprint 2 | Anton Hedlund | 712020:991ea2e9-c055-4d6e-a6b7-a44bccafe0a6 | SCRUM-64 | 1
10072 | 2026-09-21 11:00:01 | 2026-09-21 | 2026-W39 | SCRUM Sprint 2 | Calvin Koch | 712020:1793fffe-a3b4-4b8b-b162-77b2e79e19da | SCRUM-58 | 1.5
10073 | 2026-09-21 11:00:04 | 2026-09-21 | 2026-W39 | SCRUM Sprint 2 | Einar Eriksson Wahlin | 712020:873506cb-9f09-47b4-8689-67e320ded9be | SCRUM-58 | 1.5
10074 | 2026-09-21 12:29:25 | 2026-09-21 | 2026-W39 | SCRUM Sprint 2 | Anton Hedlund | 712020:991ea2e9-c055-4d6e-a6b7-a44bccafe0a6 | SCRUM-58 | 1.5
10075 | 2026-09-21 11:00:00 | 2026-09-21 | 2026-W39 | SCRUM Sprint 2 | Sai Suchith Kurra | 712020:7a155d42-06e0-4222-9d4e-f39dede68758 | SCRUM-58 | 1.5 | Team Meeting
10076 | 2026-09-21 11:00:29 | 2026-09-21 | 2026-W39 | SCRUM Sprint 2 | Seleman Hassan | 712020:7e8593ee-4747-44a1-89c2-28e81af19f99 | SCRUM-58 | 1.5
10317 | 2026-09-21 11:00:00 | 2026-09-21 | 2026-W39 | SCRUM Sprint 2 | Klas Widebeck | 712020:ba6fc434-9839-4353-a732-a8f4b60b9695 | SCRUM-58 | 1.5
10326 | 2026-09-15 08:37:00 | 2026-09-15 | 2026-W38 | SCRUM Sprint 2 | Calvin Koch | 712020:1793fffe-a3b4-4b8b-b162-77b2e79e19da | SCRUM-55 | 3
10110 | 2026-09-23 10:41:54 | 2026-09-23 | 2026-W39 | SCRUM Sprint 2 | Einar Eriksson Wahlin | 712020:873506cb-9f09-47b4-8689-67e320ded9be | SCRUM-54 | 1
10143 | 2026-09-23 20:15:50 | 2026-09-23 | 2026-W39 | SCRUM Sprint 2 | Anton Hedlund | 712020:991ea2e9-c055-4d6e-a6b7-a44bccafe0a6 | SCRUM-54 | 0.5
10318 | 2026-09-23 11:08:00 | 2026-09-23 | 2026-W39 | SCRUM Sprint 2 | Klas Widebeck | 712020:ba6fc434-9839-4353-a732-a8f4b60b9695 | SCRUM-54 | 0.5
10360 | 2026-09-11 17:24:00 | 2026-09-11 | 2026-W37 | SCRUM Sprint 1 | Sai Suchith Kurra | 712020:7a155d42-06e0-4222-9d4e-f39dede68758 | SCRUM-54 | 3
10883 | 2026-09-16 18:19:00 | 2026-09-16 | 2026-W38 | SCRUM Sprint 2 | Einar Eriksson Wahlin | 712020:873506cb-9f09-47b4-8689-67e320ded9be | SCRUM-53 | 0.5
10882 | 2026-09-16 16:49:00 | 2026-09-16 | 2026-W38 | SCRUM Sprint 2 | Einar Eriksson Wahlin | 712020:873506cb-9f09-47b4-8689-67e320ded9be | SCRUM-52 | 2
10320 | 2026-09-18 11:53:00 | 2026-09-18 | 2026-W38 | SCRUM Sprint 2 | Seleman Hassan | 712020:7e8593ee-4747-44a1-89c2-28e81af19f99 | SCRUM-50 | 4
10808 | 2026-09-29 07:47:00 | 2026-09-29 | 2026-W40 | SCRUM Sprint 3 | Seleman Hassan | 712020:7e8593ee-4747-44a1-89c2-28e81af19f99 | SCRUM-50 | 2.5
10536 | 2026-10-04 13:27:59 | 2026-10-04 | 2026-W40 | SCRUM Sprint 3 | Anton Hedlund | 712020:991ea2e9-c055-4d6e-a6b7-a44bccafe0a6 | SCRUM-49 | 5
10000 | 2026-09-16 07:44:48 | 2026-09-16 | 2026-W38 | SCRUM Sprint 2 | Sai Suchith Kurra | 712020:7a155d42-06e0-4222-9d4e-f39dede68758 | SCRUM-48 | 1
10001 | 2026-09-16 07:54:24 | 2026-09-16 | 2026-W38 | SCRUM Sprint 2 | Calvin Koch | 712020:1793fffe-a3b4-4b8b-b162-77b2e79e19da | SCRUM-48 | 1
10002 | 2026-09-16 05:54:42 | 2026-09-16 | 2026-W38 | SCRUM Sprint 2 | Einar Eriksson Wahlin | 712020:873506cb-9f09-47b4-8689-67e320ded9be | SCRUM-48 | 1
10003 | 2026-09-16 08:14:29 | 2026-09-16 | 2026-W38 | SCRUM Sprint 2 | Seleman Hassan | 712020:7e8593ee-4747-44a1-89c2-28e81af19f99 | SCRUM-48 | 1
10004 | 2026-09-16 08:18:46 | 2026-09-16 | 2026-W38 | SCRUM Sprint 2 | Anton Hedlund | 712020:991ea2e9-c055-4d6e-a6b7-a44bccafe0a6 | SCRUM-48 | 1
10037 | 2026-09-16 08:00:00 | 2026-09-16 | 2026-W38 | SCRUM Sprint 2 | Klas Widebeck | 712020:ba6fc434-9839-4353-a732-a8f4b60b9695 | SCRUM-48 | 1
10070 | 2026-09-21 08:29:54 | 2026-09-21 | 2026-W39 | SCRUM Sprint 2 | Calvin Koch | 712020:1793fffe-a3b4-4b8b-b162-77b2e79e19da | SCRUM-47 | 3
10809 | 2026-10-05 07:56:00 | 2026-10-05 | 2026-W41 | SCRUM Sprint 3 | Seleman Hassan | 712020:7e8593ee-4747-44a1-89c2-28e81af19f99 | SCRUM-46 | 1.5
10843 | 2026-09-17 16:36:00 | 2026-09-17 | 2026-W38 | SCRUM Sprint 2 | Klas Widebeck | 712020:ba6fc434-9839-4353-a732-a8f4b60b9695 | SCRUM-46 | 4
10988 | 2026-09-17 07:53:00 | 2026-09-17 | 2026-W38 | SCRUM Sprint 2 | Anton Hedlund | 712020:991ea2e9-c055-4d6e-a6b7-a44bccafe0a6 | SCRUM-46 | 1
10215 | 2026-09-14 09:17:00 | 2026-09-14 | 2026-W38 | SCRUM Sprint 2 | Sai Suchith Kurra | 712020:7a155d42-06e0-4222-9d4e-f39dede68758 | SCRUM-38 | 1
10984 | 2026-09-14 10:30:00 | 2026-09-14 | 2026-W38 | SCRUM Sprint 2 | Anton Hedlund | 712020:991ea2e9-c055-4d6e-a6b7-a44bccafe0a6 | SCRUM-37 | 1
10282 | 2026-09-27 17:42:22 | 2026-09-27 | 2026-W39 | SCRUM Sprint 2 | Anton Hedlund | 712020:991ea2e9-c055-4d6e-a6b7-a44bccafe0a6 | SCRUM-35 | 3
10249 | 2026-09-25 15:00:19 | 2026-09-25 | 2026-W39 | SCRUM Sprint 2 | Anton Hedlund | 712020:991ea2e9-c055-4d6e-a6b7-a44bccafe0a6 | SCRUM-34 | 0.25
10248 | 2026-09-25 14:15:02 | 2026-09-25 | 2026-W39 | SCRUM Sprint 2 | Anton Hedlund | 712020:991ea2e9-c055-4d6e-a6b7-a44bccafe0a6 | SCRUM-33 | 1
10881 | 2026-09-15 16:45:00 | 2026-09-15 | 2026-W38 | SCRUM Sprint 2 | Einar Eriksson Wahlin | 712020:873506cb-9f09-47b4-8689-67e320ded9be | SCRUM-28 | 2
10987 | 2026-09-11 06:50:00 | 2026-09-11 | 2026-W37 | SCRUM Sprint 1 | Anton Hedlund | 712020:991ea2e9-c055-4d6e-a6b7-a44bccafe0a6 | SCRUM-28 | 2
10214 | 2026-09-11 09:14:00 | 2026-09-11 | 2026-W37 | SCRUM Sprint 1 | Sai Suchith Kurra | 712020:7a155d42-06e0-4222-9d4e-f39dede68758 | SCRUM-27 | 2
10985 | 2026-09-14 11:00:00 | 2026-09-14 | 2026-W38 | SCRUM Sprint 2 | Anton Hedlund | 712020:991ea2e9-c055-4d6e-a6b7-a44bccafe0a6 | SCRUM-20 | 1
10990 | 2026-09-17 08:00:00 | 2026-09-17 | 2026-W38 | SCRUM Sprint 2 | Anton Hedlund | 712020:991ea2e9-c055-4d6e-a6b7-a44bccafe0a6 | SCRUM-20 | 1
10880 | 2026-09-21 13:00:00 | 2026-09-21 | 2026-W39 | SCRUM Sprint 2 | Einar Eriksson Wahlin | 712020:873506cb-9f09-47b4-8689-67e320ded9be | SCRUM-18 | 1
10315 | 2026-09-28 08:36:42 | 2026-09-28 | 2026-W40 | SCRUM Sprint 3 | Einar Eriksson Wahlin | 712020:873506cb-9f09-47b4-8689-67e320ded9be | SCRUM-17 | 2.5
10316 | 2026-09-27 19:00:00 | 2026-09-27 | 2026-W39 | SCRUM Sprint 2 | Klas Widebeck | 712020:ba6fc434-9839-4353-a732-a8f4b60b9695 | SCRUM-17 | 5
10321 | 2026-09-26 06:56:00 | 2026-09-26 | 2026-W39 | SCRUM Sprint 2 | Seleman Hassan | 712020:7e8593ee-4747-44a1-89c2-28e81af19f99 | SCRUM-17 | 5
10359 | 2026-09-26 15:23:00 | 2026-09-26 | 2026-W39 | SCRUM Sprint 2 | Sai Suchith Kurra | 712020:7a155d42-06e0-4222-9d4e-f39dede68758 | SCRUM-17 | 5.5
10364 | 2026-09-24 19:34:00 | 2026-09-24 | 2026-W39 | SCRUM Sprint 2 | Calvin Koch | 712020:1793fffe-a3b4-4b8b-b162-77b2e79e19da | SCRUM-16 | 1
10361 | 2026-09-07 19:57:00 | 2026-09-07 | 2026-W37 | SCRUM Sprint 1 | Calvin Koch | 712020:1793fffe-a3b4-4b8b-b162-77b2e79e19da | SCRUM-15 | 0.5
10367 | 2026-09-11 18:54:00 | 2026-09-11 | 2026-W37 | SCRUM Sprint 1 | Calvin Koch | 712020:1793fffe-a3b4-4b8b-b162-77b2e79e19da | SCRUM-13 | 2
10213 | 2026-09-11 09:42:00 | 2026-09-11 | 2026-W37 | SCRUM Sprint 1 | Sai Suchith Kurra | 712020:7a155d42-06e0-4222-9d4e-f39dede68758 | SCRUM-12 | 0.5
10362 | 2026-09-10 19:29:00 | 2026-09-10 | 2026-W37 | SCRUM Sprint 1 | Calvin Koch | 712020:1793fffe-a3b4-4b8b-b162-77b2e79e19da | SCRUM-12 | 1
10989 | 2026-09-11 07:57:00 | 2026-09-11 | 2026-W37 | SCRUM Sprint 1 | Anton Hedlund | 712020:991ea2e9-c055-4d6e-a6b7-a44bccafe0a6 | SCRUM-12 | 1
10366 | 2026-09-10 20:22:00 | 2026-09-10 | 2026-W37 | SCRUM Sprint 1 | Calvin Koch | 712020:1793fffe-a3b4-4b8b-b162-77b2e79e19da | SCRUM-11 | 0.5
10071 | 2026-09-18 09:14:00 | 2026-09-18 | 2026-W38 | SCRUM Sprint 2 | Sai Suchith Kurra | 712020:7a155d42-06e0-4222-9d4e-f39dede68758 | SCRUM-10 | 2.5 | The issue has been resolved.
10403 | 2026-09-29 07:44:17 | 2026-09-29 | 2026-W40 | SCRUM Sprint 3 | Sai Suchith Kurra | 712020:7a155d42-06e0-4222-9d4e-f39dede68758 | SCRUM-9 | 3.5
10369 | 2026-09-16 19:56:00 | 2026-09-16 | 2026-W38 | SCRUM Sprint 2 | Calvin Koch | 712020:1793fffe-a3b4-4b8b-b162-77b2e79e19da | SCRUM-7 | 1
10437 | 2026-09-10 11:00:00 | 2026-09-10 | 2026-W37 | SCRUM Sprint 1 | Klas Widebeck | 712020:ba6fc434-9839-4353-a732-a8f4b60b9695 | SCRUM-7 | 5

## Dim_Sprints
sprint_id | sprint_name | state | theoretical_start_date | theoretical_end_date | effective_start_date | effective_end_date
2 | SCRUM Sprint 1 | closed | 2026-08-31 00:00:00 | 2026-09-13 23:59:59 | 2026-08-31 00:00:00 | 2026-09-13 23:59:59
35 | SCRUM Sprint 2 | closed | 2026-09-14 00:00:00 | 2026-09-27 23:59:59 | 2026-09-14 00:00:00 | 2026-09-27 23:59:59
68 | SCRUM Sprint 3 | closed | 2026-09-28 00:00:00 | 2026-10-11 23:59:59 | 2026-09-28 00:00:00 | 2026-10-11 23:59:59

## Dim_Issues
issue_key | summary | issue_type | status | timespent_hours | created | updated | issue_url
SCRUM-90 | Show license for photos in-game | Bug | Done | 5 | 2026-10-10 18:53:30 | 2026-10-16 19:04:30 | https://group-six-uppsala.atlassian.net/browse/SCRUM-90
SCRUM-89 | Make a Readme | Task | To Do | 0 | 2026-10-09 12:26:17 | 2026-10-09 12:26:17 | https://group-six-uppsala.atlassian.net/browse/SCRUM-89
SCRUM-88 | Fix D3 Issues for Resubmission | Task | Done | 1 | 2026-10-08 22:04:14 | 2026-10-08 22:05:19 | https://group-six-uppsala.atlassian.net/browse/SCRUM-88
SCRUM-87 | Level 3 | Epic | To Do | 0 | 2026-10-07 14:13:56 | 2026-10-07 14:13:56 | https://group-six-uppsala.atlassian.net/browse/SCRUM-87
SCRUM-86 | Level 2 | Epic | To Do | 0 | 2026-10-07 14:13:50 | 2026-10-07 14:13:50 | https://group-six-uppsala.atlassian.net/browse/SCRUM-86
SCRUM-85 | Change the en/ett button in level 2 to separate the en/ett input | Task | Done | 5 | 2026-10-07 14:11:37 | 2026-10-10 18:54:00 | https://group-six-uppsala.atlassian.net/browse/SCRUM-85
SCRUM-84 | Correct and resubmit D3 | Bug | Done | 3.5 | 2026-10-07 13:07:21 | 2026-10-13 10:31:22 | https://group-six-uppsala.atlassian.net/browse/SCRUM-84
SCRUM-83 | Meeting 7.10.2026 | Bug | Done | 7.5 | 2026-10-07 12:47:48 | 2026-10-15 14:37:53 | https://group-six-uppsala.atlassian.net/browse/SCRUM-83
SCRUM-82 | Update the User Interface. | Task | Done | 4 | 2026-09-29 13:16:11 | 2026-10-10 18:43:02 | https://group-six-uppsala.atlassian.net/browse/SCRUM-82
SCRUM-81 | Project Management | Epic | To Do | 0 | 2026-09-28 23:02:03 | 2026-09-28 23:02:04 | https://group-six-uppsala.atlassian.net/browse/SCRUM-81
SCRUM-80 | Project Management 2 Meeting | Task | Done | 2 | 2026-09-28 22:59:42 | 2026-09-28 23:01:15 | https://group-six-uppsala.atlassian.net/browse/SCRUM-80
SCRUM-79 | Worklog Report Solution | Task | Done | 3 | 2026-09-28 22:55:55 | 2026-10-07 13:08:15 | https://group-six-uppsala.atlassian.net/browse/SCRUM-79
SCRUM-78 | Risk analysis and planning | Subtask | Done | 3 | 2026-09-28 13:38:45 | 2026-10-15 18:29:16 | https://group-six-uppsala.atlassian.net/browse/SCRUM-78
SCRUM-77 | List of potential risks | Subtask | Done | 2 | 2026-09-28 13:37:59 | 2026-10-15 18:29:14 | https://group-six-uppsala.atlassian.net/browse/SCRUM-77
SCRUM-76 | Introduction | Subtask | Done | 0 | 2026-09-28 13:37:40 | 2026-10-15 18:29:18 | https://group-six-uppsala.atlassian.net/browse/SCRUM-76
SCRUM-75 | Sprint 3 planning meeting | Task | Done | 6.5 | 2026-09-25 10:49:06 | 2026-10-15 14:37:55 | https://group-six-uppsala.atlassian.net/browse/SCRUM-75
SCRUM-74 | Look through options for time tracking | Task | Done | 1 | 2026-09-25 10:40:35 | 2026-10-07 13:08:02 | https://group-six-uppsala.atlassian.net/browse/SCRUM-74
SCRUM-73 | Prepare for Project Management and Tech Lead meeting | Task | Done | 1 | 2026-09-25 10:32:10 | 2026-10-07 14:22:59 | https://group-six-uppsala.atlassian.net/browse/SCRUM-73
SCRUM-72 | Design Level 4 | Task | To Do | 0 | 2026-09-23 14:07:23 | 2026-09-23 14:07:33 | https://group-six-uppsala.atlassian.net/browse/SCRUM-72
SCRUM-71 | Attend Technical Lead meeting 3 | Task | Done | 2 | 2026-09-23 14:05:18 | 2026-10-10 21:39:55 | https://group-six-uppsala.atlassian.net/browse/SCRUM-71
SCRUM-70 | Attend Project Management meeting 3 | Task | Done | 1 | 2026-09-23 14:05:17 | 2026-10-06 16:34:14 | https://group-six-uppsala.atlassian.net/browse/SCRUM-70
SCRUM-69 | Submit A3, Artefacts | Task | Done | 0 | 2026-09-23 14:03:04 | 2026-10-10 11:59:28 | https://group-six-uppsala.atlassian.net/browse/SCRUM-69
SCRUM-68 | Initial planning of sprint 3 | Task | Done | 1.5 | 2026-09-23 14:00:17 | 2026-10-11 20:41:39 | https://group-six-uppsala.atlassian.net/browse/SCRUM-68
SCRUM-67 | Submit D5, Integration and Project Completion Plan | Task | Done | 7 | 2026-09-23 13:59:53 | 2026-10-12 17:00:26 | https://group-six-uppsala.atlassian.net/browse/SCRUM-67
SCRUM-66 | Submit D4, Risk Assesment Plan | Task | Done | 4.5 | 2026-09-23 13:59:26 | 2026-10-12 11:32:14 | https://group-six-uppsala.atlassian.net/browse/SCRUM-66
SCRUM-65 | User Requirements | Epic | To Do | 0 | 2026-09-23 13:55:24 | 2026-09-23 13:56:06 | https://group-six-uppsala.atlassian.net/browse/SCRUM-65
SCRUM-64 | Group Meeting 24.09.2026 | Task | Done | 6 | 2026-09-23 13:48:35 | 2026-10-15 14:38:09 | https://group-six-uppsala.atlassian.net/browse/SCRUM-64
SCRUM-63 | Project Handover Code Cleanup | Epic | To Do | 0 | 2026-09-21 16:08:11 | 2026-09-21 16:08:12 | https://group-six-uppsala.atlassian.net/browse/SCRUM-63
SCRUM-62 | Meetings | Epic | To Do | 0 | 2026-09-21 16:06:13 | 2026-09-21 16:10:11 | https://group-six-uppsala.atlassian.net/browse/SCRUM-62
SCRUM-61 | Course | Epic | To Do | 0 | 2026-09-21 16:05:17 | 2026-09-21 16:09:47 | https://group-six-uppsala.atlassian.net/browse/SCRUM-61
SCRUM-60 | Level 4 Game Logic | Task | To Do | 0 | 2026-09-21 16:03:04 | 2026-09-21 16:03:56 | https://group-six-uppsala.atlassian.net/browse/SCRUM-60
SCRUM-59 | Level 4 | Epic | To Do | 0 | 2026-09-21 16:02:30 | 2026-09-21 16:09:57 | https://group-six-uppsala.atlassian.net/browse/SCRUM-59
SCRUM-58 | Group Meeting 21.09.2026 | Task | Done | 9 | 2026-09-21 14:29:42 | 2026-09-28 13:36:42 | https://group-six-uppsala.atlassian.net/browse/SCRUM-58
SCRUM-57 | add more user stories | Subtask | Done | 0 | 2026-09-21 14:16:53 | 2026-09-23 13:41:49 | https://group-six-uppsala.atlassian.net/browse/SCRUM-57
SCRUM-56 | Adjusting user requirements and adding more user stories | Subtask | Done | 0 | 2026-09-21 14:16:48 | 2026-09-23 22:58:08 | https://group-six-uppsala.atlassian.net/browse/SCRUM-56
SCRUM-55 | Reorganise the files and folders in the github repo | Task | Done | 3 | 2026-09-21 13:15:32 | 2026-09-30 12:37:29 | https://group-six-uppsala.atlassian.net/browse/SCRUM-55
SCRUM-54 | Update D2, Requirements Specification | Task | Done | 5 | 2026-09-20 18:22:35 | 2026-09-28 22:24:30 | https://group-six-uppsala.atlassian.net/browse/SCRUM-54
SCRUM-53 | Update D1, Group Agreement | Task | Done | 0.5 | 2026-09-20 18:15:13 | 2026-10-11 20:49:29 | https://group-six-uppsala.atlassian.net/browse/SCRUM-53
SCRUM-52 | Brainstorming drafts of level 4 | Task | Done | 2 | 2026-09-16 11:04:20 | 2026-10-11 20:49:14 | https://group-six-uppsala.atlassian.net/browse/SCRUM-52
SCRUM-50 | Change the en/ett button in level 3 to a field you can fill out | Task | Done | 6.5 | 2026-09-16 10:51:26 | 2026-10-16 19:04:38 | https://group-six-uppsala.atlassian.net/browse/SCRUM-50
SCRUM-49 | Fix issue with language change not affecting instructions | Bug | In Progress | 5 | 2026-09-16 10:46:54 | 2026-10-10 11:59:32 | https://group-six-uppsala.atlassian.net/browse/SCRUM-49
SCRUM-48 | Sprint planning meeting | Task | Done | 6 | 2026-09-16 10:43:45 | 2026-09-21 16:06:21 | https://group-six-uppsala.atlassian.net/browse/SCRUM-48
SCRUM-47 | Fix issue with the educational information page | Bug | Done | 3 | 2026-09-16 10:39:28 | 2026-09-30 12:38:00 | https://group-six-uppsala.atlassian.net/browse/SCRUM-47
SCRUM-46 | Look through the existing code | Task | Done | 6.5 | 2026-09-16 10:26:40 | 2026-10-13 10:53:46 | https://group-six-uppsala.atlassian.net/browse/SCRUM-46
SCRUM-45 | Write Submission | Subtask | Done | 0 | 2026-09-14 18:29:10 | 2026-09-14 18:29:18 | https://group-six-uppsala.atlassian.net/browse/SCRUM-45
SCRUM-44 | Write Submission | Subtask | Done | 0 | 2026-09-14 18:28:48 | 2026-09-14 18:29:01 | https://group-six-uppsala.atlassian.net/browse/SCRUM-44
SCRUM-43 | Write Submission | Subtask | Done | 0 | 2026-09-14 18:28:35 | 2026-09-14 18:28:42 | https://group-six-uppsala.atlassian.net/browse/SCRUM-43
SCRUM-42 | Write Submission | Subtask | Done | 0 | 2026-09-14 18:28:17 | 2026-09-14 18:28:28 | https://group-six-uppsala.atlassian.net/browse/SCRUM-42
SCRUM-41 | Write Submission | Subtask | Done | 0 | 2026-09-14 18:28:07 | 2026-09-14 18:30:21 | https://group-six-uppsala.atlassian.net/browse/SCRUM-41
SCRUM-40 | Attend Meeting | Subtask | Done | 0 | 2026-09-14 18:26:58 | 2026-09-14 18:27:10 | https://group-six-uppsala.atlassian.net/browse/SCRUM-40
SCRUM-39 | Attend Meeting | Subtask | Done | 0 | 2026-09-14 18:26:47 | 2026-09-14 18:27:07 | https://group-six-uppsala.atlassian.net/browse/SCRUM-39
SCRUM-38 | Attend Meeting | Subtask | Done | 1 | 2026-09-14 18:26:32 | 2026-09-25 12:17:19 | https://group-six-uppsala.atlassian.net/browse/SCRUM-38
SCRUM-37 | Attend Meeting | Subtask | Done | 1 | 2026-09-14 18:26:05 | 2026-10-13 10:25:19 | https://group-six-uppsala.atlassian.net/browse/SCRUM-37
SCRUM-36 | Submit A2, Artefacts | Task | Done | 0 | 2026-09-14 17:45:50 | 2026-09-28 13:34:01 | https://group-six-uppsala.atlassian.net/browse/SCRUM-36
SCRUM-35 | Ethical Considerations | Subtask | Done | 3 | 2026-09-14 16:26:10 | 2026-09-30 12:43:14 | https://group-six-uppsala.atlassian.net/browse/SCRUM-35
SCRUM-34 | Functional Requirements 2 | Subtask | Done | 0.25 | 2026-09-14 16:25:56 | 2026-09-30 12:43:12 | https://group-six-uppsala.atlassian.net/browse/SCRUM-34
SCRUM-33 | Functional Requirements 1 | Subtask | Done | 1 | 2026-09-14 16:25:41 | 2026-09-30 12:43:11 | https://group-six-uppsala.atlassian.net/browse/SCRUM-33
SCRUM-32 | Components | Subtask | Done | 0 | 2026-09-14 16:25:35 | 2026-09-30 12:43:08 | https://group-six-uppsala.atlassian.net/browse/SCRUM-32
SCRUM-31 | Definitions | Subtask | Done | 0 | 2026-09-14 16:25:28 | 2026-09-30 12:43:01 | https://group-six-uppsala.atlassian.net/browse/SCRUM-31
SCRUM-30 | Scope Statement | Subtask | Done | 0 | 2026-09-14 16:25:21 | 2026-09-30 12:43:00 | https://group-six-uppsala.atlassian.net/browse/SCRUM-30
SCRUM-29 | User Requirements 2 | Subtask | Done | 0 | 2026-09-14 14:14:13 | 2026-09-14 14:17:18 | https://group-six-uppsala.atlassian.net/browse/SCRUM-29
SCRUM-28 | User Requirements 1 | Subtask | Done | 4 | 2026-09-14 14:14:02 | 2026-10-13 10:51:31 | https://group-six-uppsala.atlassian.net/browse/SCRUM-28
SCRUM-27 | User Classes | Subtask | Done | 2 | 2026-09-14 14:13:58 | 2026-09-25 12:14:32 | https://group-six-uppsala.atlassian.net/browse/SCRUM-27
SCRUM-26 | Layout and Ethical Concerns | Subtask | Done | 0 | 2026-09-14 14:13:52 | 2026-09-14 14:17:08 | https://group-six-uppsala.atlassian.net/browse/SCRUM-26
SCRUM-20 | Attend Meeting | Subtask | Done | 2 | 2026-09-14 14:07:22 | 2026-10-13 11:00:42 | https://group-six-uppsala.atlassian.net/browse/SCRUM-20
SCRUM-19 | Attend Technical Meeting | Task | Done | 0 | 2026-09-14 14:06:09 | 2026-09-14 14:07:44 | https://group-six-uppsala.atlassian.net/browse/SCRUM-19
SCRUM-18 | Attend Project Management Meeting | Task | Done | 1 | 2026-09-14 14:05:54 | 2026-10-11 20:44:25 | https://group-six-uppsala.atlassian.net/browse/SCRUM-18
SCRUM-17 | Submit D3, Requirements Specification | Task | Done | 18 | 2026-09-14 11:38:16 | 2026-09-28 22:43:58 | https://group-six-uppsala.atlassian.net/browse/SCRUM-17
SCRUM-16 | Scope Statement | Subtask | Done | 1 | 2026-09-14 11:34:01 | 2026-09-28 22:35:13 | https://group-six-uppsala.atlassian.net/browse/SCRUM-16
SCRUM-15 | Client Meeting (online) | Task | Done | 0.5 | 2026-09-14 11:32:26 | 2026-09-28 22:28:42 | https://group-six-uppsala.atlassian.net/browse/SCRUM-15
SCRUM-14 | Submit A1, Artefacts | Task | Done | 0 | 2026-09-07 12:36:46 | 2026-09-14 18:29:29 | https://group-six-uppsala.atlassian.net/browse/SCRUM-14
SCRUM-13 | Submit D2, Requirements Elicitation | Task | Done | 2 | 2026-09-07 12:34:14 | 2026-09-28 22:55:02 | https://group-six-uppsala.atlassian.net/browse/SCRUM-13
SCRUM-12 | Submit D1, Group Agreement | Task | Done | 2.5 | 2026-09-07 12:31:35 | 2026-10-13 10:57:22 | https://group-six-uppsala.atlassian.net/browse/SCRUM-12
SCRUM-11 | Revisit the group agreement | Task | Done | 0.5 | 2026-09-04 12:43:07 | 2026-09-28 22:52:55 | https://group-six-uppsala.atlassian.net/browse/SCRUM-11
SCRUM-10 | Fix issue with level 1 | Bug | Done | 2.5 | 2026-09-04 11:57:26 | 2026-09-30 12:37:26 | https://group-six-uppsala.atlassian.net/browse/SCRUM-10
SCRUM-9 | Fix duplicate word issue in level 2 | Bug | Done | 3.5 | 2026-09-04 11:54:17 | 2026-10-10 18:43:09 | https://group-six-uppsala.atlassian.net/browse/SCRUM-9
SCRUM-7 | Fix case-sensitivity issue | Bug | Done | 6 | 2026-09-04 11:52:58 | 2026-09-30 12:36:51 | https://group-six-uppsala.atlassian.net/browse/SCRUM-7
SCRUM-4 | Subtask 2.1 | Subtask | To Do | 0 | 2026-09-02 16:12:55 | 2026-09-02 16:12:55 | https://group-six-uppsala.atlassian.net/browse/SCRUM-4

## Dim_Authors
account_id | display_name | firstname | lastname
712020:1793fffe-a3b4-4b8b-b162-77b2e79e19da | Calvin Koch | Calvin | Koch
712020:991ea2e9-c055-4d6e-a6b7-a44bccafe0a6 | Anton Hedlund | Anton | Hedlund
712020:ba6fc434-9839-4353-a732-a8f4b60b9695 | Klas Widebeck | Klas | Widebeck
712020:7e8593ee-4747-44a1-89c2-28e81af19f99 | Seleman Hassan | Seleman | Hassan
712020:873506cb-9f09-47b4-8689-67e320ded9be | Einar Eriksson Wahlin | Einar | Eriksson Wahlin
712020:7a155d42-06e0-4222-9d4e-f39dede68758 | Suchith Sai Kurra | Suchith | Sai Kurra